There are two kinds of prep nights. One option also includes coaches, who practice the puzzles that the teams will get. That option is especially handy, if many parents don’t know whether they want to be coaches or theatric. However, because there are online videos to train coaches, it is an option to focus a prep night only on the theatric volunteers. This is the agenda for that option…

## Volunteer Prep Night Agenda

Here’s what to present to the parents who attend your information night for your school’s Math Night Adventure. We recommend pitching this event as mandatory, especially for the volunteers who will be actors – they need to be familiar with their scripts before the night of the event. If someone cannot attend, make sure that the items below are covered with them somehow, at least in email.

The Volunteer Prep Night should happen 3-7 days before the event. It’s important that the Volunteer Coordinator and the Station Leads all attend, so that you can break into groups.

##### How does the Math Night Adventure play out?

Quick recap of the flow of the event, from setup to cleanup (assuming a 6pm kick-off).

- Date (usually this coming Thursday or Friday)

- Leads setup stations (4-5pm)

- Volunteer arrival time (5:30pm)

- Teams arrive in the cafeteria, and find their table (5:30pm)

- Eat dinner!

- Event starts with an opening skit (6pm)

- Every team will visit all 4 stations, although not all in the same order.
Each station takes about 30 minutes: 20 minutes of puzzle solving and 10 minutes of theatrics

- Event ends (8pm)

- Cleaned up and out of school (8:30)

##### Primary goals: fun!

- Math needs to be a fun difficulty. Not too hard. Not too easy.

- Not competitive. No winners. Coaches and mentors can help out as needed.

- Critical that teams see all 4 stations, so it’s ok to adjust math level for the sake of speed.

- Actors should be as dramatic as possible.

##### Outline the main job categories

- Actors will be interacting with kids and will be helping provide the payoff for the math the kids have done during each puzzle.

- The set-up and clean-up jobs are all about making sure that the school is treated well.

- Math mentors are also roaming the cafeteria floor and helping teams that get stuck.

- Coaches must stick with their teams at all times.

- Math mentors and Coaches should watch the online videos about the puzzles in advance. Links should be sent out by the Registrar.

##### Story overview

- Explain to everyone how every station works, and what the storyline is. 
It really helps if everyone works together to understand the overall narrative, so that they can better understand how their part fits in. This also helps the set-up volunteers understand why it’s so important to arrive on time, and to help set up the stations adequately.

- Assign Roles.

##### Split up into stations

- Actors and station helpers meet with their Theatric Station Lead.

- Mentors, setup- and cleanup helpers meet with the Puzzle Solving Station Lead.

##### Theatric stations

- Give the staff for each station a copy of their instructions and script. Review those together.

- Review arrival times and costumes.

- Dinner: encourage staff to bring dinner and/or snacks to feed themselves. If your children will have food in the cafeteria, where they solve puzzles, plan to sneak off for 10 minutes just before the event starts, to grab a bite. Or consider teaming up with your station-mates to get a pizza or the like.

##### Puzzle solving station

- The primary setup task is making sure tables are ready well before teams arrive.

- Clean-up volunteers are instrumental in ensuring that the school and its resources are respected and put right at the end of the evening – it’s a really important job.

- Review the school’s garbage capacity. If insufficient, make an announcement at the beginning, and again at the end of the adventure, ask participating teams to take any food trash home with them.

- Review the narrative with mentors. Discuss how to help with math while staying in character.

- Point mentors to online puzzle training videos, and also to QR code answer links (also mentioned in the videos).

- If there are no questions or concerns, this group can be let go once the above items have been covered.

##### Thanks for coming!